## Product Backlog
Product Backlog — CropXpert: IoT + ML Precision Agriculture Platform ¦ CINTEL, SRMIST Kattankulathur ¦ Team: Adnan Nagdiwala & Chandra Bhayal ¦ Guide: Dr. R. Siva
ID | Title | Epic | Sprint | User Story | Priority (MoSCoW) | Status | Acceptance Criteria | Functional Requirements | Non-Functional Requirements | Original Estimate | Actual Effort
1 | NPK Sensor Integration | IoT Sensor Module | Sprint 1 | As a farmer, I want the system to automatically read Nitrogen, Phosphorus, and Potassium levels from my soil so that I don't need to visit a lab. | Must | Done | 1. RS485 NPK sensor data is read every 60 seconds. 2. N, P, K values are displayed in mg/kg. 3. Values update on the web dashboard in real-time. | Interface RS485 NPK sensor via MAX485 module to Arduino UNO. Parse Modbus RTU response. Transmit data over serial/MQTT. | Sensor read latency < 2 s. Data loss rate < 0.1%. Works at soil temperatures 5–45°C. | 5 days | 5 days
2 | Soil pH Sensor Integration | IoT Sensor Module | Sprint 1 | As a farmer, I want to know my soil's pH level in real time so that I can understand soil acidity without any lab test. | Must | Done | 1. pH value read from analog pin A0. 2. Reading displayed with ±0.1 resolution. 3. Alert shown if pH is outside optimal range (5.5–7.5). | Connect analog pH sensor to Arduino A0. Calibrate using buffer solutions (pH 4, 7, 10). Map analog voltage to pH scale. | Accuracy ±0.1 pH units. Response time < 3 s. Calibration must survive power cycle. | 3 days | 3 days
3 | Soil Moisture Sensor Integration | IoT Sensor Module | Sprint 1 | As a farmer, I want real-time soil moisture readings so that I can make timely irrigation decisions. | Must | Done | 1. Moisture percentage displayed (0–100%). 2. Capacitive sensor used for corrosion resistance. 3. Low-moisture alert triggered below 25%. | Connect capacitive soil moisture sensor to Arduino analog pin. Convert raw ADC value to volumetric moisture percentage. Publish via MQTT. | Sensor lifespan > 2 years in-field. Read frequency configurable (default 60 s). Accuracy ±3%. | 3 days | 3 days
4 | DHT22 Temperature & Humidity Integration | IoT Sensor Module | Sprint 1 | As a system, I need temperature and humidity data so that the ML model has all required input features. | Must | Done | 1. Temperature and humidity polled every 30 s. 2. Values shown on dashboard alongside soil readings. 3. Sensor failure triggers a dashboard alert. | Integrate DHT22 with Arduino digital pin. Implement retry logic for failed reads. Send values to MQTT broker. | Temperature accuracy ±0.5°C. Humidity accuracy ±2–5%. Continuous uptime > 99% over 30-day test period. | 2 days | 2 days
5 | Rainfall Data Auto-Fetch (OpenWeatherMap) | IoT Sensor Module | Sprint 1 | As a farmer, I want rainfall data fetched automatically using my location so that I don't have to enter it manually. | Must | Done | 1. API call made using farmer's GPS coordinates. 2. 7-day average rainfall returned in mm. 3. Fallback to manual entry if API fails. | Integrate OpenWeatherMap One Call API. Parse precipitation field. Cache results for 6 hours to avoid rate-limit. | API response time < 3 s. Graceful fallback on network failure. Cached value served within 50 ms. | 3 days | 3 days
6 | Dataset Collection & Preprocessing | ML Recommendation Engine | Sprint 2 | As a developer, I want a clean, representative Indian crop dataset so that the ML model generalises well across Indian agro-climatic zones. | Must | Done | 1. Dataset contains ≥2,200 samples across 22 Indian crops. 2. No missing values after preprocessing. 3. Train/val/test split is 70/15/15 stratified. | Download Kaggle Crop Recommendation Dataset. Augment with ICAR regional soil data. Apply Z-score outlier removal. Fit and serialise StandardScaler. | Class balance ≤1.5× ratio. Scaler saved separately for inference. Preprocessing pipeline is reproducible via script. | 4 days | 4 days
7 | Random Forest Model Training | ML Recommendation Engine | Sprint 2 | As a system, I need a trained Random Forest model so that crop recommendations are accurate and fast. | Must | Done | 1. Model achieves ≥99% accuracy on test set. 2. Inference time < 5 ms per prediction. 3. Model file size < 100 MB. | Train Random Forest with GridSearchCV (100–500 estimators, max_depth tuning). 5-fold cross-validation. Serialise model with joblib. | Accuracy ≥99.2% on 22-class test set. Model size ≤10 MB. Reproducible via seed=42. | 5 days | 5 days
8 | Multi-Model Comparison (XGBoost, SVM, MLP, LightGBM) | ML Recommendation Engine | Sprint 2 | As a developer, I want to compare multiple ML models so that I can select the best-performing one for production. | Should | Done | 1. All 5 models evaluated on same test split. 2. Comparison table showing Accuracy, Precision, Recall, F1. 3. Best model selected and documented. | Train XGBoost, SVM (RBF), MLP (128-64-32), LightGBM. Use same preprocessing pipeline. Export metrics to CSV. | Evaluation is reproducible. Confusion matrix saved for each model. Report generated automatically. | 6 days | 6 days
9 | ML API Endpoint (FastAPI) | ML Recommendation Engine | Sprint 2 | As a web application, I need a REST API endpoint so that sensor data can be sent and crop predictions returned in JSON. | Must | In Progress | 1. POST /predict accepts 7-feature JSON input. 2. Returns top-3 crops with confidence scores. 3. Returns HTTP 422 for invalid inputs. | Build FastAPI app. Load serialised RF model and scaler at startup. Validate input with Pydantic. Return JSON response. | API response time < 200 ms (p95). Handles 50 concurrent requests. Input validation rejects out-of-range values. | 4 days | 3 days
10 | Top-3 Crop Recommendations with Confidence Scores | ML Recommendation Engine | Sprint 2 | As a farmer, I want to see the top 3 crop recommendations with their confidence scores so that I have options to choose from. | Must | In Progress | 1. Dashboard shows top-3 crops ranked by confidence. 2. Confidence shown as percentage with colour-coded bar. 3. Clicking a crop shows its sowing and care tips. | Use predict_proba from RF model. Sort descending. Map crop index to name dictionary. Return top 3. | All 3 recommendations returned within 200 ms. Confidence percentages sum to ≤100%. Crop names localised per language setting. | 3 days | 2 days
11 | AGMARKNET MSP Data Integration | Market Intelligence Layer | Sprint 3 | As a farmer, I want to see the current Minimum Support Price for recommended crops so that I can choose crops that are both soil-suitable and economically viable. | Must | Pending | 1. MSP data fetched for all 22 crops from AGMARKNET API. 2. Data refreshed every 24 hours. 3. MSP displayed alongside crop recommendation. | Integrate AGMARKNET REST API. Parse commodity MSP fields. Cache in SQLite with 24-hour TTL. Display ₹/quintal alongside recommendation. | API failure must not break recommendation flow (graceful degradation). Cache hit rate > 90% during normal operation. | 5 days | -
12 | Weighted Market-Agronomic Scoring Function | Market Intelligence Layer | Sprint 3 | As a farmer, I want the system to balance soil suitability and market price so that I get recommendations that are both agronomically and financially optimal. | Must | Pending | 1. Final score = 0.60×ML_prob + 0.25×MSP_Index + 0.15×SeasonDemand. 2. Weights configurable in admin settings. 3. Score breakdown shown in detailed view. | Implement scoring formula in Python. Normalise MSP values as index (0–1). Combine with ML probability. Re-rank top-3 output. | Score computation adds < 50 ms to response. Formula weights validated by domain expert (agricultural officer). Unit tested with mock data. | 4 days | -
13 | Mandi Price Trend Graphs | Market Intelligence Layer | Sprint 3 | As a farmer, I want to see 3-month price trend charts for recommended crops so that I can time my selling decision. | Should | Backlog | 1. Line chart shows last 90 days of mandi prices. 2. Chart loads within 2 s. 3. Chart is interactive (hover shows date and price). | Pull historical price data from AGMARKNET. Store in SQLite. Render chart with Chart.js on the frontend. | Chart renders within 2 s on 3G connection. Data sourced from at least 3 mandis per crop. Mobile-responsive. | 5 days | -
14 | Government Scheme Advisory Module | Farmer Support Portal | Sprint 3 | As a farmer, I want to see government welfare schemes I am eligible for so that I can access PM-KISAN, crop insurance, and other benefits. | Must | Pending | 1. At least 6 schemes displayed with eligibility, benefits, documents, and apply link. 2. Schemes filtered by farmer's state. 3. Content updated from MyScheme.gov.in API monthly. | Build Scheme model in database. Populate with PM-KISAN, PM Fasal Bima Yojana, Soil Health Card, PMKSY, KCC, state subsidies. Render as card layout. | Scheme data must be accurate as of current month. Apply links must be live government URLs. Page load < 3 s. | 5 days | -
15 | Loan & Financial Guidance Module | Farmer Support Portal | Sprint 3 | As a farmer, I want clear guidance on low-interest and zero-interest agricultural loans so that I can make informed financing decisions. | Must | Backlog | 1. At least 5 loan programs listed (KCC, NABARD, state waivers). 2. Each entry shows interest rate, eligibility, and application steps. 3. EMI calculator available for KCC loans. | Create Loan model. Populate KCC (0–4% interest), NABARD schemes, PM Formalization micro-food processing. Build EMI calculator component. | Loan information reviewed and approved by faculty advisor. EMI calculator validated against RBI formula. No broken links. | 4 days | -
16 | Farming Campaign & Awareness Section | Farmer Support Portal | Sprint 4 | As a farmer, I want access to training content on modern farming so that I can improve my techniques sustainably. | Could | Backlog | 1. At least 10 articles/videos on organic farming, fertigation, drip irrigation. 2. Content searchable by topic. 3. Content available in all 4 supported languages. | Create Article model with title, content, language, tags. Build search with full-text indexing. Admin panel for content management. | Page load < 3 s. Search returns results < 1 s. Content accessible on 2G connection (text-first). | 6 days | -
17 | Farm Profit Calculator | Farmer Support Portal | Sprint 4 | As a farmer, I want to estimate profit per crop per acre before planting so that I can make the best financial decision. | Should | Backlog | 1. Calculator takes crop, acreage, and location as input. 2. Outputs estimated input cost, yield, market price, and net profit. 3. Results shown as comparison table for top-3 recommended crops. | Build profit estimation logic using AGMARKNET prices and standard input cost data (per crop per state). Render as interactive table. | Calculation completes < 1 s. Input cost data sourced from State Agriculture Department reports. Mobile-friendly layout. | 4 days | -
18 | Multilingual UI — Hindi, Marathi, Tamil, Telugu | Multilingual Interface | Sprint 4 | As a farmer with limited English literacy, I want to use the entire platform in my native language so that I can understand all recommendations and advice. | Must | Pending | 1. Full UI available in Hindi, Marathi, Tamil, Telugu. 2. Language auto-detected from browser locale. 3. Manual toggle persisted in user profile. | Implement i18n with React-i18next. Build JSON translation files for all 4 languages. Localise crop names, scheme descriptions, advisory text. Validate translations with native speakers. | Language switch completes < 500 ms. Zero untranslated strings in production build. RTL layout not required (all 4 languages are LTR). | 8 days | -
19 | Vernacular Crop Advisory Text | Multilingual Interface | Sprint 4 | As a farmer, I want crop-specific sowing tips, care guidelines, and harvest timing shown in my language so that I can act on the recommendation immediately. | Should | Backlog | 1. Each crop has sowing month, fertiliser schedule, and harvest window. 2. Text displayed in selected language. 3. Advisory validated by agricultural domain expert. | Create CropAdvisory model with fields for each language. Populate for all 22 crops. Link to recommendation output API. | Advisory text reviewed by KVK agricultural officer. No machine-translation errors for key agronomic terms. Displays correctly on mobile. | 6 days | -
20 | WhatsApp CropBot (Twilio Integration) | CropBot — WhatsApp & SMS | Sprint 4 | As a farmer with a smartphone but no computer, I want to get crop recommendations via WhatsApp so that I can use the system from my field. | Must | Pending | 1. Farmer sends soil values in natural language via WhatsApp. 2. Bot parses N, P, K, pH, moisture values from message. 3. Bot replies with top-3 crops + MSP price + sowing tip within 10 s. | Integrate Twilio WhatsApp API with FastAPI webhook. Build NLP parser for multilingual input (Hindi/English). Connect to ML prediction endpoint. Format and return response. | Bot response time < 10 s end-to-end. Handles malformed input gracefully. Supports Hindi and English input. Uptime > 99.5%. | 7 days | -
21 | SMS Shortcode Fallback Bot | CropBot — WhatsApp & SMS | Sprint 4 | As a farmer with a basic keypad phone and no internet, I want to get recommendations via SMS so that I am not excluded from the platform. | Should | Backlog | 1. Farmer texts: CROP N90 P42 K43 PH6.5 DIST PUNE 2. System parses values and returns top-1 crop + price via SMS. 3. Works from any GSM phone without data connection. | Integrate MSG91 SMS API. Define shortcode format parser. Connect to ML API. Format reply within 160-character SMS limit. | SMS delivered within 60 s. Parser handles missing fields with defaults. Cost per SMS < ₹0.10. Tested on Airtel, Jio, BSNL networks. | 5 days | -
22 | Soil Health Trend Logging (SQLite) | Soil Health Dashboard | Sprint 2 | As a farmer, I want my soil readings saved over time so that I can see if my soil health is improving or degrading. | Must | In Progress | 1. Every sensor reading stored with timestamp and location. 2. Data retained for minimum 2 years. 3. User can download their data as CSV. | Create SensorReading model in SQLite. Auto-insert on every MQTT message. Implement CSV export endpoint. | Write latency < 50 ms. Storage footprint < 1 MB per farm per month. Export handles up to 10,000 rows. | 3 days | 2 days
23 | Soil Health Traffic-Light Dashboard | Soil Health Dashboard | Sprint 3 | As a farmer, I want a simple visual dashboard showing whether each nutrient is in the healthy range so that I can immediately understand my soil status. | Must | Pending | 1. Dashboard shows N, P, K, pH, moisture each with Red/Amber/Green indicator. 2. Thresholds based on crop-specific optimal ranges. 3. Dashboard refreshes every 60 s. | Build React dashboard component. Define threshold constants per crop. Map sensor values to RAG status. Implement auto-refresh. | Dashboard loads < 2 s. Threshold data peer-reviewed by agricultural officer. Accessible to colour-blind users (icons supplement colour). | 4 days | -
24 | Fertiliser Dose Recommendation | Soil Health Dashboard | Sprint 3 | As a farmer, I want the system to recommend how much fertiliser to apply based on my soil deficiency so that I don't over- or under-fertilise. | Should | Backlog | 1. Recommendation shows fertiliser type, quantity per acre, and timing. 2. Based on deficiency relative to crop-specific optimal NPK. 3. Cost estimate in INR included. | Implement deficiency calculation (optimal − measured). Map to fertiliser product (Urea for N, DAP for P, MOP for K). Calculate dose per acre using standard ICAR dosage tables. | Fertiliser recommendations validated against ICAR crop nutrition guidelines. Cost data updated monthly from market prices. No recommendation if sensor data is stale > 24 h. | 4 days | -
25 | React Frontend — Core Dashboard | Web Application & PWA | Sprint 2 | As a farmer, I want a clean, mobile-friendly web dashboard showing all my sensor readings and recommendations in one place. | Must | In Progress | 1. Dashboard shows live NPK, pH, moisture, temp readings. 2. Crop recommendation card visible on homepage. 3. Responsive on mobile (375px–1440px width). | Build React app with component: SensorCard, RecommendationCard, LanguageToggle, NavBar. Use CSS Grid for responsive layout. | Lighthouse mobile score > 80. First Contentful Paint < 2 s on 3G. No horizontal scroll on 375px viewport. | 8 days | 5 days
26 | Progressive Web App (PWA) — Offline Support | Web Application & PWA | Sprint 4 | As a farmer in a low-connectivity area, I want the app to work offline so that I can still view my last recommendations without internet. | Should | Backlog | 1. App installable on Android home screen. 2. Last recommendation and soil readings accessible offline. 3. Data syncs automatically when connection restores. | Configure Service Worker with Workbox. Cache static assets and last API response. Implement background sync for pending submissions. | Offline mode functional for core features. Cache size < 10 MB. Sync completes within 30 s of reconnection. | 5 days | -
27 | User Authentication & Farm Profile | Web Application & PWA | Sprint 2 | As a farmer, I want to create a profile with my farm location and details so that recommendations are personalised to my region. | Must | In Progress | 1. Farmer can register with mobile number + OTP. 2. Profile stores name, state, district, land size. 3. Location used to auto-fetch rainfall and mandi data. | Implement OTP auth via MSG91. Create Farmer model (name, mobile, state, district, acreage, language preference). JWT token authentication. | OTP delivery < 30 s. Session token expires in 7 days. HTTPS enforced. Password/OTP never stored in plain text. | 5 days | 4 days
28 | ESP32 Microcontroller Migration | LoRa + ESP32 Extension | Sprint 5 | As a system architect, I want to migrate from Arduino UNO to ESP32 so that we get built-in Wi-Fi, Bluetooth, and higher processing power. | Could | Backlog | 1. All sensor code ported from Arduino to ESP32 (MicroPython or C++). 2. Built-in Wi-Fi used instead of external ESP8266. 3. OTA firmware update capability added. | Port sensor interfaces to ESP32 GPIO. Test all 4 sensors on ESP32 WROOM-32. Enable Arduino OTA library. Document pin mapping. | All sensors functional on ESP32 with same accuracy. OTA update completes < 60 s. Power consumption < 250 mA during sensing cycle. | 7 days | -
29 | LoRa SX1276 Communication Module | LoRa + ESP32 Extension | Sprint 5 | As a farmer in a remote village without 4G, I want my sensor data to reach the cloud via LoRa so that I can use CropXpert without internet. | Won't | Backlog | 1. Sensor data transmitted via LoRa SX1276 at 915 MHz. 2. Range > 5 km in open field conditions. 3. LoRaWAN gateway receives data and forwards to backend. | Integrate LoRa SX1276 with ESP32 SPI bus. Implement LoRaWAN OTAA join. Deploy RAK2245 gateway. Configure TTN (The Things Network) application. | Packet delivery rate > 95% at 5 km range. Power consumption < 20 mA in transmit mode. Data payload ≤ 51 bytes (LoRaWAN limit). | 10 days | -
30 | PM-WANI Backhaul Integration | LoRa + ESP32 Extension | Sprint 5 | As a system, I want to use PM-WANI public Wi-Fi as backhaul for the LoRaWAN gateway so that deployment costs are minimised in rural areas. | Won't | Backlog | 1. Gateway connects to PM-WANI hotspot automatically. 2. Fallback to mobile data if PM-WANI unavailable. 3. Connectivity status visible in admin dashboard. | Configure gateway network priority: PM-WANI Wi-Fi → 4G SIM → 3G SIM. Implement connectivity health check. Admin alert on prolonged disconnect. | Gateway reconnects within 60 s of network change. Supports WPA2 for PM-WANI. Tested in field with Jio and Airtel PM-WANI hotspots. | 6 days | -

## Sprint Summary
CropXpert — Sprint Summary & Roadmap
Sprint | Epic(s) Covered | Key Deliverables | Story Count | Total Estimate | Status
Sprint 1 (Weeks 1–2) | IoT Sensor Module | NPK + pH + Moisture + DHT22 sensors integrated. Rainfall API live. MQTT streaming to backend. | 5 | 16 days | Done
Sprint 2 (Weeks 3–4) | ML Engine + Web App + Soil Logging | RF model trained (99.2%). FastAPI /predict endpoint. React dashboard. SQLite trend logging. User auth/profile. | 6 | 25 days | In Progress
Sprint 3 (Weeks 5–6) | Market Layer + Farmer Portal + Soil Dashboard | AGMARKNET MSP integration. Weighted scoring. Govt scheme portal. Fertiliser advisor. Traffic-light dashboard. | 6 | 22 days | Pending
Sprint 4 (Weeks 7–8) | Multilingual UI + CropBot + PWA + Farming Campaigns | Hindi/Marathi/Tamil/Telugu UI. WhatsApp + SMS bots. Offline PWA. Profit calculator. Campaign section. | 7 | 35 days | Backlog
Sprint 5 (Future Release) | LoRa + ESP32 Extension | ESP32 migration. LoRa SX1276 5–15 km connectivity. PM-WANI backhaul. 1,000-node LoRaWAN gateway. | 3 | 23 days | Backlog

## MoSCoW Summary
CropXpert — MoSCoW Priority Summary
Priority | Count | Story IDs | Description
Must | 14 | 1–10, 11–12, 14–15, 18, 20, 22–23, 25, 27 | Core non-negotiable features: all sensor integrations, ML engine, market layer, multilingual UI, WhatsApp bot, soil dashboard, web app, auth.
Should | 10 | 13, 16–17, 19, 21, 24, 26, 28 | Important features that significantly enhance value: mandi trend charts, profit calculator, SMS bot, fertiliser advisor, PWA offline, ESP32 migration.
Could | 4 | 16, 28, 29 | Desirable but not essential: farming campaigns, ESP32 OTA updates, LoRa SX1276 module.
Won't | 2 | 29, 30 | Out of scope for current release: LoRa hardware deployment, PM-WANI backhaul integration (planned for v2.0).