## Release Plan
CropXpert — Release Plan / Roadmap 2026
Epic / Feature | Sprint 1 (Jan 2026) |  |  |  | Sprint 2 (Feb 2026) |  |  |  | Sprint 3 (Mar 2026) |  |  |  | Sprint 4 (Apr 2026) |  |  |  | Sprint 5 (May 2026)
| W / 1 | W / 2 | W / 3 | W / 4 | W / 1 | W / 2 | W / 3 | W / 4 | W / 1 | W / 2 | W / 3 | W / 4 | W / 1 | W / 2 | W / 3 | W / 4 | W / 1 | W / 2 | W / 3 | W / 4
IoT Sensor Module | Sprint 2 (Feb 2026) W / 1: ✓ DONE Sprint 1
ML Recommendation Engine | Sprint 2 (Feb 2026) W / 4: IN PROGRESS
Market Intelligence Layer | Sprint 4 (Apr 2026) W / 1: PENDING
Govt Scheme & Loan Portal | Sprint 4 (Apr 2026) W / 1: PENDING
Multilingual Interface | Sprint 5 (May 2026) W / 1: BACKLOG
CropBot (WhatsApp / SMS) | Sprint 5 (May 2026) W / 1: BACKLOG
Soil Health Dashboard | Sprint 3 (Mar 2026) W / 3: IN PROGRESS
Web App & PWA | Sprint 5 (May 2026) W / 1: Sprint 2 – 4
LoRa Extension (v2.0 Roadmap) | Sprint 5 (May 2026) W / 4: ROADMAP
Legend: | Sprint 1 (Jan 2026) W / 2: Done; Sprint 2 (Feb 2026) W / 1: In Progress; Sprint 2 (Feb 2026) W / 4: Pending; Sprint 3 (Mar 2026) W / 3: Backlog; Sprint 4 (Apr 2026) W / 2: Cross-Sprint; Sprint 5 (May 2026) W / 1: Roadmap v2.0