## Sheet1
CropXpert — Sprint 1 Retrospective ¦ CINTEL, SRMIST Kattankulathur ¦ Adnan Nagdiwala & Chandra Bhayal ¦ Guide: Dr. R. Siva
Sprint Retrospective — Sprint 1 (IoT Sensor Module) · Weeks 1–2 · 16 Story Points · Status: DONE ✓
What Went Well | What Went Poorly | What Ideas Do You Have | How Should We Take Action | Category
Successes and positive outcomes from Sprint 1. Practices and achievements the team should continue. | Challenges, blockers, and failures encountered in Sprint 1. Areas that need improvement. | New approaches, tools, or strategies to improve efficiency and avoid repeating issues. | Specific, actionable steps assigned to address issues and implement improvements for Sprint 2. | Guidelines
All 4 sensors (RS485 NPK, pH, Capacitive Moisture, DHT22) successfully integrated with Arduino UNO within Sprint 1 timeline. MAX485 RS485-to-TTL conversion worked first attempt with correct wiring. Modbus RTU parsing logic completed cleanly with retry logic for failed reads. Sensor read latency confirmed < 2 s — meeting the non-functional requirement. | Initial RS485 NPK sensor returned garbage values — took 1.5 days to debug baud rate mismatch (9600 vs 4800). DHT22 produced occasional NaN reads under 3.3V; required pull-up resistor fix. Capacitive moisture calibration drifted between dry-air and wet-soil tests. | Add automated sensor self-test on startup — validate each sensor returns a sane value before beginning normal polling. Document exact wiring diagram with pin labels for reproducibility across future hardware units. | Adnan: Write startup validation script by Sprint 2 Week 1. Chandra: Finalize and commit wiring diagram (Fritzing) to GitHub by end of Sprint 1. Both: Standardise calibration procedure and store calibration constants in EEPROM. | Hardware / IoT
MQTT broker (Mosquitto) deployed and ESP8266 publishing JSON sensor payloads reliably within 2 days of hardware integration. MQTT message format agreed and documented: topic cropxpert/farm/<id>/sensors. Data loss rate measured at 0.04% over 48-hour test — well within 0.1% requirement. | ESP8266 Wi-Fi reconnection after power cycle took up to 45 s in first build; farmer context means power cuts are common. MQTT broker ran on localhost; no TLS configured yet — security gap identified. | Implement ESP8266 persistent Wi-Fi credentials in EEPROM with auto-reconnect loop capped at 10 s before fallback to stored last reading. Enable MQTT TLS with self-signed cert in Sprint 2 — broker already supports it. | Adnan: Implement EEPROM Wi-Fi + MQTT reconnect logic — PR by Sprint 2 Day 3. Chandra: Configure Mosquitto TLS with Let's Encrypt cert on cloud server. Both: Add reconnect metric to dashboard — show last-seen timestamp per sensor node. | Communication / MQTT
OpenWeatherMap OneCall API integration completed in 1 day. GPS-based auto-fetch of 7-day average rainfall working correctly. 6-hour cache in SQLite confirmed — avoids rate-limiting on free tier (1,000 calls/day). Graceful fallback to manual rainfall entry tested and working. | Free-tier API key accidentally committed to GitHub — caught in code review and rotated immediately. No breach, but process gap identified. API response sometimes returns null precipitation field for certain districts — edge case not handled in v1. | Move all API keys to environment variables / .env file with dotenv; add .env to .gitignore — enforce via pre-commit hook. Handle null precipitation field with zero default + UI warning label. | Chandra: Set up GitHub Secrets for all API keys before Sprint 2 starts. Adnan: Add null-safe precipitation parsing with warning banner on dashboard. Both: Add pre-commit hook (detect-secrets) to repo — block accidental key commits. | External APIs
Daily stand-ups (15 min, WhatsApp voice) kept both members aligned. GitHub branching strategy (feature branches + PR review) worked smoothly — zero merge conflicts in Sprint 1. Sprint 1 completed all 5 stories on schedule — 16 story points, 16 days. Velocity: 1.0 points/day (baseline established). Guide Dr. R. Siva review session completed — received positive feedback. | No formal Definition of Done agreed before sprint — acceptance criteria were interpreted differently by team members for Story 3 (moisture sensor). Sprint planning underestimated debugging time for hardware issues by ~30%. No CI/CD pipeline yet — builds and tests run manually. | Define and sign-off a formal DoD checklist before Sprint 2 begins: code reviewed, unit tested, merged, demo-ready. Add 20% buffer to all hardware-related story estimates going forward. Set up GitHub Actions CI pipeline for linting + unit tests in Sprint 2. | Both: Write DoD checklist (max 8 items) and paste into Notion before Sprint 2 kickoff. Adnan: Add 20% buffer to Sprint 2 hardware stories during planning. Chandra: Set up GitHub Actions workflow (Python lint + pytest) by Sprint 2 Day 2. | Team Process
All Sprint 1 acceptance criteria met and signed off: Story 1: NPK reads N/P/K in mg/kg, latency < 2 s ✓ Story 2: pH ±0.1 accuracy, alert on out-of-range ✓ Story 3: Moisture 0–100%, low-moisture alert < 25% ✓ Story 4: DHT22 polling with retry logic ✓ Story 5: Rainfall API with 6h cache + fallback ✓ SQLite sensor_reading table created and receiving data. Sprint 2 backlog (ML Engine + React dashboard + User Auth) groomed and ready. | Sprint 2 ML model training dataset not yet downloaded — Story 6 (dataset preprocessing) is Sprint 2 Day 1 dependency. React project scaffolding not started — Story 25 (React dashboard) will need environment setup time at Sprint 2 start. No unit tests written for sensor parsing functions in Sprint 1 — technical debt. | Dedicate first 2 hours of Sprint 2 Day 1 to: (1) Kaggle dataset download, (2) React CRA scaffold, (3) FastAPI project structure — unblock all stories. Write pytest unit tests for all Sprint 1 sensor parsing functions as tech-debt payoff in Sprint 2 first week. | Adnan: Download Kaggle Crop Recommendation Dataset + run EDA notebook — commit to repo by Sprint 2 Day 1 EOD. Chandra: Scaffold React app with routing, state management, i18n stub — PR by Sprint 2 Day 2. Both: Write 10 unit tests for Sprint 1 sensor parsing — merge by Sprint 2 Day 3. | Sprint 2 Readiness
SPRINT 1 METRICS — Stories Completed: 5/5 ¦ Story Points: 16/16 ¦ Velocity: 1.0 pt/day ¦ Defects: 3 found, 3 resolved ¦ Sprint Status: DONE ✓
SPRINT 2 COMMITMENT — Stories Planned: 6 ¦ Points: 25 ¦ Epics: ML Engine · React PWA · Soil Logging · User Auth ¦ Target: Guide Demo Ready
CropXpert Minor Project · Dept. of CINTEL, SRMIST Kattankulathur · Adnan Nagdiwala (119) & Chandra Bhayal (072) · Guide: Dr. R. Siva · AY 2024–25